## Gantt Chart Template
TASK TITLE | TASK OWNER | START DATE | DUE DATE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
|  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Basic Movement Player | Alex | 2022-10-18 | bar: WEEK 1 W to WEEK 1 R
Base State Machine | Adrià | 2022-10-18 | bar: WEEK 1 W to WEEK 1 R
Animations Collaiders Player | Alejandro | 2022-10-18 | bar: WEEK 1 W to WEEK 2 F
State Machine Air | Adrià | 2022-10-20 | bar: WEEK 1 F to WEEK 2 F
Double Jump + Others | Alex | 2022-10-20 | bar: WEEK 1 F to WEEK 2 F
Basic Enemys | Alejandro | 2022-10-21
State Machine Atacks Basics | Adrià | 2022-10-22
Drag wall | Alex | 2022-10-22
Enemy Walk | Alejandro | 2022-10-23
Crouch | Alex | 2022-10-24 | bar: WEEK 2 M to WEEK 3 M
State Machine Crouch | Adrià | 2022-10-24 | bar: WEEK 2 M to WEEK 3 T
Enemy Shoot Basic | Alejandro | 2022-10-26 | bar: WEEK 2 M to WEEK 3 W
Crouch | Alex | 2022-10-27 | bar: WEEK 3 T to WEEK 3 F
State Machine Combos | Adrià | 2022-10-27 | bar: WEEK 3 T to WEEK 3 R
Enemy Shoot Basic | Alejandro | 2022-10-29 | bar: WEEK 3 R to WEEK 3 F
Interaction Enemy-Player | Adrià | 2022-10-30 | bar: WEEK 3 F to WEEK 4 T
Enemy Shoot HomeLeader + Mele | Alejandro | 2022-10-31 | bar: WEEK 4 M to WEEK 4 T
Map | Alex | 2022-10-31 | bar: WEEK 4 M to WEEK 4 T